Keerthana P

Exp. No: 10

PROGRAM 1:

import numpy as np

import networkx as nx

import matplotlib.pyplot as plt

# Task data

tasks = {

'A': {'optimistic': 1, 'most_likely': 3, 'pessimistic': 5, 'dependencies': []},

'B': {'optimistic': 2, 'most_likely': 4, 'pessimistic': 6, 'dependencies': ['A']},

'C': {'optimistic': 1, 'most_likely': 2, 'pessimistic': 3, 'dependencies': ['A']},

'D': {'optimistic': 2, 'most_likely': 3, 'pessimistic': 4, 'dependencies': ['B']},

'E': {'optimistic': 3, 'most_likely': 6, 'pessimistic': 9, 'dependencies': ['C']},

'F': {'optimistic': 2, 'most_likely': 5, 'pessimistic': 8, 'dependencies': ['D', 'E']}

}

# Compute expected duration & variance

for task, data in tasks.items():

data['expected_duration'] = (

data['optimistic'] + 4 * data['most_likely'] + data['pessimistic']

) / 6

data['variance'] = (

(data['pessimistic'] - data['optimistic']) / 6

) ** 2

# Create graph

G = nx.DiGraph()

for task, data in tasks.items():

G.add_node(task, duration=data['expected_duration'], variance=data['variance'])

for dep in data['dependencies']:

G.add_edge(dep, task)

# Topological order

topological_order = list(nx.topological_sort(G))

# Forward pass

earliest_start = {task: 0 for task in topological_order}

earliest_finish = {task: 0 for task in topological_order}

for task in topological_order:

earliest_finish[task] = earliest_start[task] + G.nodes[task]['duration']

for succ in G.successors(task):

earliest_start[succ] = max(earliest_start[succ], earliest_finish[task])

# Backward pass

latest_finish = {task: earliest_finish[task] for task in topological_order}

latest_start = {task: earliest_start[task] for task in topological_order}

for task in reversed(topological_order):

for pred in G.predecessors(task):

latest_finish[pred] = min(latest_finish[pred], latest_start[task])

latest_start[pred] = latest_finish[pred] - G.nodes[pred]['duration']

# Critical path

critical_path = [

task for task in topological_order

if earliest_start[task] == latest_start[task]

]

# Project duration & std deviation

project_duration = earliest_finish[topological_order[-1]]

project_variance = sum(G.nodes[t]['variance'] for t in critical_path)

project_std_dev = np.sqrt(project_variance)

# Output

print("Earliest Start:", earliest_start)

print("Earliest Finish:", earliest_finish)

print("Latest Start:", latest_start)

print("Latest Finish:", latest_finish)

print("Critical Path:", critical_path)

print("Project Duration:", project_duration)

print("Project Std Deviation:", project_std_dev)

# Graph

pos = nx.spring_layout(G)

nx.draw(G, pos, with_labels=True, node_color='orange', node_size=3000)

nx.draw_networkx_edge_labels(

G, pos,

edge_labels={(u, v): f"{u}->{v}" for u, v in G.edges}

)

plt.show()

Output:

Earliest Start: {'A': 0, 'B': 3, 'C': 3, 'D': 7, 'E': 5, 'F': 11}

Earliest Finish: {'A': 3, 'B': 7, 'C': 5, 'D': 10, 'E': 11, 'F': 16}

Latest Start: {'A': 0, 'B': 3, 'C': 5, 'D': 7, 'E': 7, 'F': 11}

Latest Finish: {'A': 3, 'B': 7, 'C': 7, 'D': 10, 'E': 13, 'F': 16}

Critical Path: ['A', 'B', 'D', 'F']

Project Duration: 16.0

Project Std Deviation: 1.29

PROGRAM 2:

import numpy as np

import networkx as nx

# Task data

tasks = {

'A': {'o': 2, 'm': 3, 'p': 8, 'dep': []},

'B': {'o': 1, 'm': 4, 'p': 7, 'dep': ['A']},

'C': {'o': 2, 'm': 5, 'p': 8, 'dep': ['A']},

'D': {'o': 3, 'm': 6, 'p': 9, 'dep': ['B']},

'E': {'o': 2, 'm': 4, 'p': 6, 'dep': ['C']},

'F': {'o': 3, 'm': 7, 'p': 11, 'dep': ['D', 'E']}

}

# Compute expected time & variance

for t in tasks:

o, m, p = tasks[t]['o'], tasks[t]['m'], tasks[t]['p']

tasks[t]['te'] = (o + 4*m + p) / 6

tasks[t]['var'] = ((p - o) / 6) ** 2

# Build graph

G = nx.DiGraph()

for t in tasks:

G.add_node(t, duration=tasks[t]['te'], variance=tasks[t]['var'])

for d in tasks[t]['dep']:

G.add_edge(d, t)

# Topological order

order = list(nx.topological_sort(G))

# Forward pass

ES = {t: 0 for t in order}

EF = {}

for t in order:

EF[t] = ES[t] + G.nodes[t]['duration']

for succ in G.successors(t):

ES[succ] = max(ES.get(succ, 0), EF[t])

# Backward pass

LF = {t: EF[t] for t in order}

LS = {}

for t in reversed(order):

LS[t] = LF[t] - G.nodes[t]['duration']

for pred in G.predecessors(t):

LF[pred] = min(LF.get(pred, float('inf')), LS[t])

# Critical path

CP = [t for t in order if abs(ES[t] - LS[t]) < 1e-6]

# Project duration & std deviation

project_duration = EF[order[-1]]

project_variance = sum(G.nodes[t]['variance'] for t in CP)

project_std = np.sqrt(project_variance)

# Output

print("Earliest Start:", ES)

print("Earliest Finish:", EF)

print("Critical Path:", CP)

print("Project Duration:", project_duration)

print("Standard Deviation:", project_std)

Output:

Earliest Start: {'A': 0, 'B': 3.5, 'C': 3.5, 'D': 7.5, 'E': 8.0, 'F': 13.0}

Earliest Finish: {'A': 3.5, 'B': 7.5, 'C': 8.0, 'D': 13.0, 'E': 12.0, 'F': 20.0}

Critical Path: ['A', 'B', 'D', 'F']

Project Duration: 20.0

Standard Deviation: 1.53